## Sheet1
MODULE-I
DOCUMENT INTELLIGENCE
UI TASKS | DURATION | INTERGRATION | ALLOCATED TO | STATUS
Creating user Login Page with EmailID and password - Login Button | 150 | 120 | Jitesh | New
Designing Admin Home page with navigation bar with logout and Client, Add Users link button | 150 | - | Jitesh | New
Designing Add Client button and new form to add new client - ClientName , Email-Id , Default Password | 150 | 240 | Jitesh | New
In upload tab - give options to upload multiple files- status must be loaded as list | 240 | 480 | Jitesh
Analyze button covert to background job for - multiple files - store in DB | 240 | 240 | Jitesh
Displaying the sorted docs , extracted data from DB- patient already exist or not field | 150 | 120 | Jitesh
Check if the client is a qsecure client - should map if true | 120 | - | Jitesh
If new patient then check qualification - if qualified for new setup | 120 | - | Jitesh
TOTAL DAYS | 3 | 3
API TASKS | DURATION | INTERGRATION | ALLOCATED TO | STATUS
API for adding new admin- Login | 240 | - | Kiruba | New
API to add client for the particular admin | 150 | - | Kiruba | New
API to update and delete the Clients or roles or user based | 240 | - | Kiruba | New
In upload tab - give options to upload multiple files- status must be loaded as list | 240 | - | Kiruba
Analyze button convert to background job for - multiple files - store in DB | 480 | - | Kiruba
Check if the client is a qsecure client - should map if true- name , isQsecure status | 480 | - | Kiruba
Displaying the sorted docs , extracted data from DB- patient already exist or not field | 480 | - | Kiruba
Get status from uploaded file - input List<Guid> | 240 | - | Kiruba
TOTAL DAYS | 6
TARGET DATE: | 2024-11-19 |  | 9
4.5
Get Unprocessed fax from Qsecure for a client ID and get patient details for new setup | 480
Create dynamic rule master prompt for all document categories | 480
Check if the patient is new setup qualified with new setup data | 480
Update edited patient data extracted in DB in separate collection. | 240