## Sheet2
MODULE-I
DOCUMENT INTELLIGENCE
UI TASKS | DURATION | INTERGRATION | ALLOCATED TO | STATUS
Creating user Login Page with EmailID and password - Login Button | 150 | 120 | Jitesh | New
Designing Admin Home page with navigation bar with logout and Client, Add Users link button | 150 | - | Jitesh | New
Designing Add Client button and new form to add new client - ClientName , Email-Id , Default Password | 150 | 240 | Jitesh | New
In upload tab - give options to upload multiple files- status must be loaded as list | 240 | 480 | Jitesh
Analyze button covert to background job for - multiple files - store in DB | 240 | 240 | Jitesh
Displaying the sorted docs , extracted data from DB- patient already exist or not field | 150 | 120 | Jitesh
Check if the client is a qsecure client - should map if true | 120 | - | Jitesh
If new patient then check qualification - if qualified for new setup | 120 | - | Jitesh
API TASKS | DURATION | INTERGRATION | ALLOCATED TO | STATUS
Create User Login API's with Login and Session handling - Create Entity
Create Roles to Add for each Users on client and admin level
Uploading Pdf files to Db and getting their status - Multiple file
Get List API to get the status List of Files for the current session
Background Job running to Analyze the multiple files
Tiff conversion for easily storing the files in DB- in API
Storing the extracted Page numbers for the respective types of documents
Storing the extracted content from the Open AI to the database
Get List API from qsecure for getting the clients - Mapping if same
Displaying API to provide page number and extracted Content for the files
API to check if patient is available in the qsecure client - requires new setup or not

## Sheet1
MODULE-I
DOCUMENT INTELLIGENCE
UI TASKS | DURATION | INTERGRATION | ALLOCATED TO | STATUS
Creating user Login Page with EmailID and password - Login Button | 150 | 120 | Jitesh | New
Designing Admin Home page with navigation bar with logout and Client, Add Users link button | 150 | - | Jitesh | New
Designing Add Client button and new form to add new client - ClientName , Email-Id , Default Password | 150 | 240 | Jitesh | New
In upload tab - give options to upload multiple files- status must be loaded as list | 240 | 480 | Jitesh
Analyze button covert to background job for - multiple files - store in DB | 240 | 240 | Jitesh
Displaying the sorted docs , extracted data from DB- patient already exist or not field | 150 | 120 | Jitesh
Check if the client is a qsecure client - should map if true | 120 | - | Jitesh
If new patient then check qualification - if qualified for new setup | 120 | - | Jitesh
TOTAL DAYS | 3 | 3
API TASKS | DURATION | INTERGRATION | ALLOCATED TO | STATUS
API for adding new admin- Login | 240 | - | Kiruba | New
API to add client for the particular admin | 150 | - | Kiruba | New
API to update and delete the Clients or roles or user based | 240 | - | Kiruba | New
In upload tab - give options to upload multiple files- status must be loaded as list | 240 | - | Kiruba
Analyze button convert to background job for - multiple files - store in DB | 480 | - | Kiruba
Check if the client is a qsecure client - should map if true- name , isQsecure status | 480 | - | Kiruba
Displaying the sorted docs , extracted data from DB- patient already exist or not field | 480 | - | Kiruba
Get status from uploaded file - input List<Guid> | 240 | - | Kiruba
TOTAL DAYS | 6
Get Unprocessed fax from Qsecure for a client ID and get patient details for new setup | 480
Create dynamic rule master prompt for all document categories | 480
Check if the patient is new setup qualified with new setup data | 480
Update edited patient data extracted in DB in separate collection. | 240